## HOW TO USE THIS
This spreadsheet is intended to give you a snapshot, and high level assessment, of your current organisational portfolio, programme and project management maturity (3PM Maturity).
It is a self-assessment tool that can be completed quickly. As it is a self-assessment tool it has an inherent bias depending on your own personal views of the organisation.
The assessment can be validated and further improved by viewing evidence for each of the statements.
The assessment can be completed by a single individual, a group, or you can collate the responses from several individuals into one spreadsheet for greater accuracy.
This assessment is not intended to take the place of a formal assessment by an external organisation or consultant.
Start with the QUESTIONS tab and go through each of the questions listed there.
Each question can be scored 0, 1, 2, 3, 4, 5 - Each scoring cell has a dropdown box with these numbers in it or you can enter the numbers manually.
Each number corresponds to the following statements:
0 - We do not need this element
1 - We do not have, or use this element, and are not aware of it at all
2 - We do not have, or use this, element but we are aware of it and probably should use it
3 - We do have, or use this element, but do not always use it appropriately and/or consistently
4 - We do have, or use this element, and use it appropriately, consistently and competently
5 - We do have, or use this element, and use it in an exemplary manner
These scoring definitions have been included at multiple points in the QUESTIONS tab so you can see them as you scroll down.
Once you have answered all the questions, your results will be available on the SUMMARY tab. Each score is between a low of 0, and a high of 5.
The spreadsheet is set to ignore scores of 0 when calculating the average score for a Topic. Therefore, a score of 0 means that you have acknowledged that you do not need any element in that Topic at all.
The radar, or spider web, chart shows Topic scores as a percentage so you can compare different areas.
The bar chart shows your overall organisational 3PM score out of 5.
Your priority areas for improvement are generally the lowest scoring areas.
If you find any errors in this spreadsheet please inform me and I will fix it and issue a new iteration.
If you need any assistance filling out this assessment, or wish to discuss a full assessment using more in-depth assessment tools, then please contact me at sean@crystal.consulting

## QUESTIONS
SCORE EXPLANATION
QUESTION | SCORE | 0 - We do not need this element
1. Does your organisation have a clear, appropriate and documented organizational strategy? |  | 1 - We do not have, or use this element, and are not aware of it at all
2. Does your organisation ensure that all approved projects contribute to achieving strategic goals? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
3. Does your organisation have senior level support for, and understanding of, project management as a strategic enabler? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
4. Does your organisation have a tailored, or customized, project management methodology or methodologies? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
5. Does your organisation describe the processes and guidelines for tailoring the project management methodology to suit individual projects? |  | 5 - We do have, or use this element, and use it in an exemplary manner
6. Does your organisation define and utilise the role of portfolio manager (or chief projects officer)?
7. Does your organisation describe how projects are selected from amongst all the potential projects that could be done?
8. Does your organisation describe how projects are justified using financial and/or non-financial metrics?
9. Does your organisation describe the contents, depth and process of developing a project business case?
10. Does your organisation describe how the project will be financed?
11. Does your organisation describe the process that determines how projects are prioritized?
12. Does your organisation describe how a project is approved including the roles that must provide approval?
13. Does your organisation describe the project phases and how the project moves across any stage gates, boundaries or notable milestones?
14. Does your organisation describe how governance is provided and the composition of the project steering group or committee?
15. Does your organisation describe the role and responsibility of the project sponsor?
16. Does your organisation define and utilise the role of program manager? |  | 0 - We do not need this element
17. Does your organisation define how management of cross project resources will be managed? |  | 1 - We do not have, or use this element, and are not aware of it at all
18. Does your organisation define how multiple projects working towards a common goal will be managed? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
19. Does your organisation describe how the level of project complexity will be determined and strategies for dealing with this? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
20. Does your organisation describe how organizational changes will be recognized, documented and managed? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
21. Does your organisation require project managers to have a tertiary level credential? |  | 5 - We do have, or use this element, and use it in an exemplary manner
22. Does your organisation require project managers to have a professional credential?
23. Does your organisation require project managers to carry out ongoing professional development?
24. Does your organisation require project managers to maintain membership of a professional association?
25. Does your organisation have internally developed and owned project management training materials?
26. Does your organisation have a defined project management career path?
27. Does your organisation have a PMO, or similar function, responsible for reporting on portfolio, program and project progress? |  | 0 - We do not need this element
28. Does your organisation have a PMO, or similar function, or similar function, that carries out audits of projects? |  | 1 - We do not have, or use this element, and are not aware of it at all
29. Does your organisation have a PMO, or similar function, that provides project management training? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
30. Does your organisation have a PMO, or similar function, that provides project governance? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
31. Does your organisation have a PMO, or similar function, that provides project sponsorship? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
32. Does your organisation have a PMO, or similar function, that provides project prioritization? |  | 5 - We do have, or use this element, and use it in an exemplary manner
33. Does your organisation have a PMO, or similar function, that provides project resourcing such as project managers and support staff?
34. Does your organisation describe the roles and levels of delegated authority for decision making on the project?
35. Does your organisation describe the main roles required on the project and their responsibilities?
36. Does your organisation describe how the project charter is prepared and authorized?
37. Does your organisation describe any software you will use to help track, estimate, report or document any part of the project?
38. Does your organisation describe the tools and techniques that will be used to monitor project performance?
39. Does your organisation describe the overall process for how requested changes will be documented and assessed?
40. Does your organisation describe the approved project change control process?
41. Does your organisation describe how project status will be reported?
42. Does your organisation describe how project configuration management and version control will occur in the project?
43. Does your organisation describe how project requirements will be gathered and documented? |  | 0 - We do not need this element
44. Does your organisation describe how project requirements will be checked, monitored and how changes to them will be assessed? |  | 1 - We do not have, or use this element, and are not aware of it at all
45. Does your organisation describe how the work breakdown structure is prepared and the format it is documented in? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
46. Does your organisation describe how the work breakdown structure will be checked, monitored and how changes to it will be assessed? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
47. Does your organisation describe how the project and product scope will be defined and documented? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
48. Does your organisation describe how the project scope will be checked, monitored and how changes to it will be assessed? |  | 5 - We do have, or use this element, and use it in an exemplary manner
49. Does your organisation describe the processes, tools and techniques used to develop a project schedule?
50. Does your organisation describe how the project schedule will be checked, monitored and how changes to it will be assessed?
51. Does your organisation describe and require the use of scheduling software?
52. Does your organisation describe the processes, tools and techniques used to estimate costs on the project? |  | 0 - We do not need this element
53. Does your organisation describe how project cost estimates will be checked, monitored and how changes to them will be assessed? |  | 1 - We do not have, or use this element, and are not aware of it at all
54. Does your organisation describe the processes, tools and techniques used to prepare and document a project budget? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
55. Does your organisation describe how the project budget forecast will be checked, monitored and how changes to it will be assessed? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
56. Does your organisation require the use of earned value management techniques for monitoring cost and/or time? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
57. Does your organisation describe any internal financial processes that may influence the project? |  | 5 - We do have, or use this element, and use it in an exemplary manner
58. Does your organisation describe and require the use of cost and budgeting software?
59. Does your organisation describe the processes for implementing quality assurance in the project?
60. Does your organisation describe how quality assurance audits will occur in the project?
61. Does your organisation describe how quality control will be defined, inspected and documented on the project?
62. Does your organisation describe how the quality management processes will be checked, monitored and how changes to them will be assessed?
63. Does your organisation describe and require the use of quality management software?
64. Does your organisation describe how the numbers and experience of people required to complete the work will be estimated? |  | 0 - We do not need this element
65. Does your organisation describe how the people required to complete the work will be monitored and changes to human resource requirements assessed? |  | 1 - We do not have, or use this element, and are not aware of it at all
66. Does your organisation describe how the project team members will be recruited, developed and managed? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
67. Does your organisation describe how project leadership skills will be developed and assessed? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
68. Does your organisation describe how project communications will be defined and documented? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
69. Does your organisation describe the processes, methods, tools and techniques for distributing project communications? |  | 5 - We do have, or use this element, and use it in an exemplary manner
70. Does your organisation describe how project communications will be monitored and how changes to the communications process will be assessed?
71. Does your organisation describe the use of communications management software?
72. Does your organisation describe how risks will be identified, documented and qualitatively assessed? |  | 0 - We do not need this element
73. Does your organisation describe how risks will be identified, documented and quantitatively assessed? |  | 1 - We do not have, or use this element, and are not aware of it at all
74. Does your organisation describe how identified risks will be monitored and how changes to the risk register will be assessed? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
75. Does your organisation describe how project issues will be documented and monitored? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
76. Does your organisation describe the use of risk management software? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
77. Does your organisation describe the processes, tools and techniques for preparing, assessing, negotiating and implementing project contracts? |  | 5 - We do have, or use this element, and use it in an exemplary manner
78. Does your organisation describe how contracts will be monitored and how changes will be assessed?
79. Does your organisation describe how suppliers to the project will be managed?
80. Does your organisation describe the processes by which contractual claims are assessed and are resolved?
81. Does your organisation describe how project stakeholders will be identified and their needs and expectations documented? |  | 0 - We do not need this element
82. Does your organisation describe the processes and strategies for managing and influencing project stakeholder expectations? |  | 1 - We do not have, or use this element, and are not aware of it at all
83. Does your organisation describe how the stakeholder register will be monitored and changes to it assessed? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
84. Does your organisation describe how the project customers’ needs will be identified and managed? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
85. Does your organisation describe the processes for determining and documenting health and safety requirements on the project? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
86. Does your organisation describe how health and safety requirements will be monitored and how changes will be assessed? |  | 5 - We do have, or use this element, and use it in an exemplary manner
87. Does your organisation describe how health and safety software will be used?
88. Does your organisation describe the processes for determining environmental requirements for the project?
89. Does your organisation describe how environmental requirements will be monitored and how changes will be assessed?
90. Does your organisation describe how the project deliverable/s will be formally accepted? |  | 0 - We do not need this element
91. Does your organisation describe the process for handover of the deliverables to operations? |  | 1 - We do not have, or use this element, and are not aware of it at all
92. Does your organisation describe the processes for defining project or phase closure? |  | 2 - We do not have, or use this, element but we are aware of it and probably should use it
93. Does your organisation describe how lessons learned will be gathered, documented and archived? |  | 3 - We do have, or use this element, but do not always use it appropriately and/or consistently
94. Does your organisation describe how expected project benefits are assessed? |  | 4 - We do have, or use this element, and use it appropriately, consistently and competently
95. Does your organisation describe the processes for conducting a post implementation review of the project? |  | 5 - We do have, or use this element, and use it in an exemplary manner

## SUMMARY
TOPIC | SCORE |  | Low | Medium | High
Organizational Project Management | 0 | 0% | 0.2 | 0.55 | 0.85
Portfolio Management | 0 | 0% | 0.2 | 0.55 | 0.85
Program Management | 0 | 0% | 0.2 | 0.55 | 0.85
Practitioner Competency and Capability Development | 0 | 0% | 0.2 | 0.55 | 0.85
Project Management Office (PMO) | 0 | 0% | 0.2 | 0.55 | 0.85
Integration Management | 0 | 0% | 0.2 | 0.55 | 0.85
Scope Management | 0 | 0% | 0.2 | 0.55 | 0.85
Time Management | 0 | 0% | 0.2 | 0.55 | 0.85
Cost Management | 0 | 0% | 0.2 | 0.55 | 0.85
Quality Management | 0 | 0% | 0.2 | 0.55 | 0.85
Human Resource Management | 0 | 0% | 0.2 | 0.55 | 0.85
Communications Management | 0 | 0% | 0.2 | 0.55 | 0.85
Risk Management | 0 | 0% | 0.2 | 0.55 | 0.85
Procurement Management | 0 | 0% | 0.2 | 0.55 | 0.85
Stakeholder Management | 0 | 0% | 0.2 | 0.55 | 0.85
Health, Safety & Environmental Management | 0 | 0% | 0.2 | 0.55 | 0.85
Project Closure | 0 | 0% | 0.2 | 0.55 | 0.85
OVERALL SCORE | 0 | 0%

## Reference (hidden)
0 | We do not need this element
1 | We do not have, or use this element, and are not aware of it at all
2 | We do not have, or use this, element but we are aware of it and probably should use it
3 | We do have, or use this element, but do not always use it appropriately and/or consistently
4 | We do have, or use this element, and use it appropriately, consistently and competently
5 | We do have, or use this element, and use it in an exemplary manner